## AttendanceManagement
Form Name | Function Name | Planned Date | Planned Hours | Start Date | Finished Date | Delayed Hour | Ahead of schedule | Total Used Hour For Finished Work | Current Condition
ViewAttendance | displayCurrentDateTime | 30/5/2025 | 7.5 | 30/5/2025 | 2025-09-06 | 7.5 | - | 15 | Done
| checkIn | 2025-09-06 | 4 | 2025-10-06 | 2025-10-06 | 7.5 | - | 4 | Done
| checkOut | 2025-09-06 | 3.5 | 2025-10-06 | 2025-10-06 | 7.5 | - | 1.5 | Done
| viewAttendance | 2025-10-06 | 7.5 | 2025-11-06 | 2025-10-06 | - | - | 2 | Done
| checkLeaveOrAbsent | 2025-11-06 | 7.5 | 2025-11-06 | 2025-11-06 | - | - | 7.5 | Done
| checkHoliday | 2025-12-06 | 3 | [5 empty] | Not yet started
| highlightRows | 2025-12-06 | 4.5 | [5 empty] | Not yet started
| searchByMonth | 13/6/2025 | 7.5 | [5 empty] | Not yet started
DailyAttendance | chooseDepartment | 16/5/2025 | 3 | [5 empty] | Not yet started
| checkHolidayLabel | 17/6/2025 | 4.5 | [5 empty] | Not yet started
| displayDailyAttendance | 18/6/2025 | 7.5 | [5 empty] | Not yet started
| searchByDate | 17/6/2025 | 7.5 | [5 empty] | Not yet started
| updateAttendance | 18/6/2025 | 7.5 | [5 empty] | Not yet started
Not Start |  | Doned | [6 empty] | Continue
DailyAttendance |  | - | [6 empty] | DailyAttendance
MonthlyAttendance

## EmployeeManagement
Control Name | Function Name | Planned Start Date | Planned End Date | Planned Hours | Start Date | Finished Date | Delayed Hour | Ahead of schedule | Total Used Hour For Finished Work | Current Condition
AddNewEmployeeControl | UploadProfilePicture | 30/5/2025 |  | 15 | 30/5/2025 | 2025-09-06 | - | - | 15 | Done
| GenerateEmployeeNumber | 2025-10-06 |  | 7.5 | 2025-10-06 | 2025-10-06 | - | 3.5 | 4 | Done
| GeneratePassword | 2025-11-06 |  | 7.5 | 2025-10-06 | 2025-10-06 | - | 7.5 | 3.5 | Done
| Load NRC data | 2025-12-06 |  | 7.5 | 2025-11-06 | 2025-12-06 | - | - | - | Done
| Validate and Add to Database | 13/6/2025 |  | 30 | 16/11/2025 | 20/6/2025 | 7.5 | - | 37.5 | Done
ViewEmployeeList(HR) | Search | 19/6/2025 |  | 7.5 | [5 empty] | Not yet started
| ShowDataGridView | 20/6/2025 |  | 7.5 | [5 empty] | Not yet started
| ViewDetails | 24/6/2025 |  | 7.5 | [5 empty] | Not yet started
| UpdateEmployeeInformation | 25/6/2025 |  | 7.5 | [5 empty] | Not yet started
ViewEmployeeList(Head) | Search | 26/6/2025 |  | 2 | [5 empty] | Not yet started
| Show DataGridView | 26/6/2025 |  | 2 | [5 empty] | Not yet started
| ViewDetails | 26/6/2025 |  | 3.5 | [5 empty] | Not yet started
ViewProfile(Admin,Head,Employee) | DisplayProfile | 27/6/2025 |  | 7.5 | [5 empty] | Not yet started
Not Start |  | Doned | [7 empty] | Continue
ViewEmployeeList |  | - | [7 empty] | ViewEmployeeList
ViewProfile