## EmployeeManagementToFix
Control Name | Process Brief | Testing | Planned Date | Planned Hour | Condition
AddNewEmployeeControl | To show position names of Sale and Marketing in each employee information details | NG2 | 2025-07-11 | 4
AddNewEmployeeControl | To show position name in ViewProfile(Head) | NG2 | 2025-07-11 | 3.5
AddNewEmployeeControl | To update termination date | NG2 | 2025-07-15 | 7.5
AddNewEmployeeControl | To validate phone Number Format | NG1 | 2025-07-16 | 7.5
AddNewEmployeeControl | To update UI design in View Profile by each role | NG1 | 2025-07-17 | 4
AddNewEmployeeControl | To validate browse button to upload profile picture | NG1 | 2025-07-17 | 3.5

## AttendanceToFix
Control Name | Process Brief | Testing | Planned Date | Planned Hour | Condition
ViewAttendanceControl | To show full day leave by checking entire leave. | NG2 | 2025-07-11 | 3.5 | Done
DailyAttendanceControl | To show full day leave by checking entire leave. | NG2 | 2025-07-11 | 2.5 | Done
CheckInOutAvailabilityLoad | To check with entire leave record not with each row. | NG2 | 2025-07-11 | 1.5 | Done
ViewAttendanceControl | To hide ActionButtonColumn in future date of current month and full day leave rows | NG2 | 2025-07-15 | 4 | Done
EmployeeSearchControl | To filter employee list according to head's deparment. | NG2 | 2025-07-15 | 3.5 | Done
EmployeeSearchControl | Choose an employee by typing valid full id or choosing from list view. | NG2 | 2025-07-16 | 3
| To Check whether the error message is exist or not. | NG2 | 2025-07-16 | 1
| If exist, display the error message again. | NG2 | 2025-07-16 | 1
| If not, retrieve from database using the selected Employee Id and month. | NG1 | 2025-07-16 | 2.5
Employee Dashboard | Month Picker and Search Button are being left alignment in maximize version. | NG1 | 2025-07-17 | 3
ViewAttendanceControl | To make current date row on top | NG1 | 2025-07-17 | 4.5

## LeaveManagementToFix
Control Name | Process Brief | Testing | Planned Date | Planned Hour | Condition
HrViewEmployeeDailyLeave | To show on leave data (Check with start date and end date) | NG2 | 2025-07-11 | 4 | Done
ViewLeaveControl (for all roles and conditions) | To set default number of rows to display. | NG1 | 2025-07-11 | 3.5 | Done
ViewLeaveControl | To make Approve, Reject and RevertStatus button not available for past date. | NG2 | 2025-07-15 | 7.5
Cancel Button | To reload Leave Request Form to available to apply after cancel leave | NG2 | 2025-07-16 | 5
SearchPanelForEmployeeId | To hide employee information suggestion listView when user pressed other key or screen. | NG1 | 2025-07-16 | 2.5

## Login,ReportToFix
Form Name | Process Brief | Testing | Planned Date | Planned Hour | Condition
Login Form | In employee ID text box, only available number | NG2 | 2025-07-11 | 1 | Done
| In Password text box, cannot copy and paste. | NG2 | 2025-07-11 | 1 | Done
| If Employee ID is not found in database, then show invalid message and focus on Employee ID TextBox. | NG2 | 2025-07-11 | 2.5 | Done
| If Employee ID is found in database, then Validate Password if Password is invalid, show invalid message and focus on Password TextBox. | NG2 | 2025-07-11 | 2.5 | Done
Daily Attendance Summary Report | The Export button should only work if data has been successfully loaded (either default or searched). | NG2 | 2025-07-15 | 1.5 | Done
| If no data is loaded, show an error message and prevent the export. | NG2 | 2025-07-15 | 2.5 | Done
| To prepare backgroundcolor if back clicked daily report tab, change backgroundcolor. | NG2 | 2025-07-15 | 1.5
| To do responsive, if minimize button clicked. | NG2 | 2025-07-15 | 2
Monthly Attendance Summary Report | Export button must only work after a successful search. | NG2 | 2025-07-16 | 2.5
| If Employee ID is empty, show error message and cannot export. | NG2 | 2025-07-16 | 1.5
| If Employee ID is empty and click search button,show error message (2 times) | NG2 | 2025-07-16 | 2
| If Search was not performed, show error message and cannot export. | NG2 | 2025-07-16 | 1.5
| Title of Monthly Attendance Summary Report need to align. | NG2 | 2025-07-17 | 1
| If employee ID is empty,data do not load in the monthly attendance summary report and export button do not work. | NG2 | 2025-07-17 | 3