## AdminForm
Admin (画面) | 機能名 | 対応中機能 | 状況 | 担当者
- Login Form | Login,Cancel |  | 完了 | NNW
- Admin Home | (Button) CheckIn,CheckOut --------------------------------------- (Label) Today Employee,Today Present, Today absence,Pending Leave | 未着手(Label ) | 完了(Button) | ZNA
- Add Employee | Save,Cancel |  | 完了 | YNW
- Employee List | Search | Order By for Employee No Filter For search |  | AMMZ
- Attendence List | Search | GridView data Binding Filter For search |  | ZNA
- Leave List | Search | Status(Waiting,Accept) |  | NNW
未着手 | 予定時間
Admin Home（Label) | 4hrs
対応中 | 予定時間
Employee List | 15 hrs
Attendence List | 4hrs
Leave List | 4 hrs
完了 | 予定時間
Login Form | -
Add Employee | -

## EmployeeForm
Employee (画面) | 機能名 | 対応中機能 | 状況 | 担当者
- Login Form | Login,Cancel |  | 完了 | NNW
- Employee Home | CheckIn,CheckOut |  | 完了 | ZNA
- Employee Profile | - |  | 完了 | YNW
- Attendence List | Search | GridView data Binding |  | ZNA
- Request Leave | Upload,Cancel |  | 完了 | NNW
- Leave List | - | 未着手 |  | NNW
未着手 | 予定時間
Leave List | 15 hrs
対応中 | 予定時間
Attendence List | 11.5 hrs
完了
Login Form
Employee Home
Employee Profile
Request Leave

## Man Hours
Date | Assigned Member | Form Name | Function Name | Plan(%) | Current Condition | Planed Used Hour | Real Condition(%) | Real Used Hour | Worked Date
2025-05-08 | NNW | Admin Leave List | Status(Waiting,Accept) | 100% | Done | ４Hrs | 100% | 4Hr | 2024-07-01
NNW