## AttendanceManagement
Form Name | Function Name | Planned Date | Planned Hours | Start Date | Finished Date | Delayed Hour | Ahead of schedule | Total Used Hour For Finished Work | Current Condition
ViewAttendance | displayCurrentDateTime | 30/5/2025 | 7.5 | 30/5/2025 | 2025-09-06 | 7.5 | - | 15 | Done
| checkIn | 2025-09-06 | 4 | 2025-10-06 | 2025-10-06 | 7.5 | - | 4 | Done
| checkOut | 2025-09-06 | 3.5 | 2025-10-06 | 2025-10-06 | 7.5 | - | 1.5 | Done
| viewAttendance | 2025-10-06 | 7.5 | 2025-11-06 | 2025-10-06 | - | - | 2 | Done
| checkLeaveOrAbsent | 2025-11-06 | 7.5 | 2025-11-06 | 2025-11-06 | - | - | 7.5 | Done
| checkHoliday | 2025-12-06 | 3 | [5 empty] | Not yet started
| highlightRows | 2025-12-06 | 4.5 | [5 empty] | Not yet started
| searchByMonth | 13/6/2025 | 7.5 | [5 empty] | Not yet started
DailyAttendance | chooseDepartment | 16/5/2025 | 3 | [5 empty] | Not yet started
| checkHolidayLabel | 17/6/2025 | 4.5 | [5 empty] | Not yet started
| displayDailyAttendance | 18/6/2025 | 7.5 | [5 empty] | Not yet started
| searchByDate | 17/6/2025 | 7.5 | [5 empty] | Not yet started
| updateAttendance | 18/6/2025 | 7.5 | [5 empty] | Not yet started
Not Start |  | Doned | [6 empty] | Continue
DailyAttendance |  | - | [6 empty] | DailyAttendance
MonthlyAttendance

## EmployeeManagement
Control Name | Function Name | Planned Date | Planned Hours | Start Date | Finished Date | Delayed Hour | Ahead of schedule | Total Used Hour For Finished Work | Current Condition
AddNewEmployeeControl | UploadProfilePicture | 30/5/2025 | 15 | 30/5/2025 | 2025-09-06 | - | - | 15 | Done
| GenerateEmployeeNumber | 2025-10-06 | 7.5 | 2025-10-06 | 2025-10-06 | - | 3.5 | 4 | Done
| GeneratePassword | 2025-11-06 | 7.5 | 2025-10-06 | 2025-10-06 | - | 7.5 | 3.5 | Done
| Validate Form | 2025-12-06 | 30 | 2025-11-06
| Add Function | 17/6/2025 | 15 | [5 empty] | Not yet started
Not yet started
Not yet started
ViewEmployeeList | Search | 19/6/2025 | 7.5 | [5 empty] | Not yet started
| ShowDataGridView | 20/6/2025 | 7.5 | [5 empty] | Not yet started
| ViewDetails | 24/6/2025 | 7.5 | [5 empty] | Not yet started
| UpdateEmployeeInformation | 25/6/2025 | 7.5 | [5 empty] | Not yet started
ViewProfile | DisplayProfile | 26/6/2025 | 7.5 | [5 empty] | Not yet started
Not Start |  | Doned | [6 empty] | Continue
ViewEmployeeList |  | - | [6 empty] | ViewEmployeeList
ViewProfile

## Admin
Form Name | Function Name | Current Condition | Assigned Member
- Login Form | Login | 完了 | SLPA
- Login Form | Save | 完了 | SLPA
Not Start |  | Continue |  | Doned
Leave List |  | Add Attendence List |  | Login Form

## Employee
Form Name | Function Name | Current Condition | Assigned Member
Not Start |  | Continue |  | Doned
Leave List |  | Add Attendence List |  | Login Form

## Department_Head
Form Name | Function Name | Function Details | Current Condition | Assigned Member
Not Start
Leave List
Continu
Add Attendence List
Doned Form
Login Form
Employee Home
Employee Profile
Request Leave