## EmployeeManagementToFix
Control Name | Process Brief | Testing Status | Planned Date | Planned Hour | Condition
AddNewEmployeeControl | To update termination date in View Employee by HR | Ng2 | 2025-07-21 | 6.5 | Done
AddNewEmployeeControl | Reload data after updating employee information | Ng2 | 2025-07-21 | 0.5 | Done
AddNewEmployeeControl | Reload data in View Employee List | Ng1 | 2025-07-21 | 0.5
AddNewEmployeeControl | If Department Head is inactive, allow to select DepartmentHead in comboBox | Ng2 | 2025-07-22 | 1.5 | Done
AddNewEmployeeControl | PopUp Message Box(title,icon,Action) | Ng1 | 2025-07-22 | 0.5 | Done | 8nLm@qAy
| Show Error Message instead of messageBox in Update form, | Ng1 | 2025-07-22 | 0.5 | Done | A5#GGqp&
| Clean radio button after clicking cancel in AddNewEmployeeForm | Ng1 | 2025-07-22 |  |  | l5l#XBSE
AddNewEmployeeControl | To validate Null Variable in AddNewEmployeeForm | Ng1 | 2025-07-22 | 0.5 | Done
AddNewEmployeeControl | Tab Order in AddNewEmployeeForm,Tab Order in ChangePassword | Ng1 | 2025-07-22 | 0.5
AddNewEmployeeControl | Resize profile picture in ViewProfile | Ng1 | 2025-07-22 | 0.5
| Disable color of input fields in View Profile | Ng1 | 2025-07-22
| Resize input fields in AddNewEmployeeForm | Ng1 | 2025-07-22
| Change Background Color in AddNewEmployeeForm | Ng1 | 2025-07-22
AddNewEmployeeControl | ComboBox Scrolling | Ng1 | 2025-07-22 | 0.5
| Can't input ComboBox | Ng1 | 2025-07-22
AddNewEmployeeControl | Date Format in datetimepicker | Ng1 | 2025-07-22 | 0.5
AddNewEmployeeControl | Overflow in input fields | Ng1 | 2025-07-22
AddNewEmployeeControl | To show Expection error | Ng1 | 2025-07-22 | 1.5
AddNewEmployeeControl | To validate input Fields in ChangePassword | Ng1 | 2025-07-22
| Error message in ChangePassword | Ng1 | 2025-07-22
AddNewEmployeeControl | To allow user to select Hired date in Future | Ng1 | 2025-07-22 | 0.5
AddNewEmployeeControl | Alignment in input fields | Ng1 | 2025-07-22
AddNewEmployeeControl | Scrollbar in InputFields(Current,Permanent) | Ng1 | 2025-07-22

## Attendance, Dashboard, Search
Control Name | Process Brief | Status | Planned Date | Planned Hour | Condition
ViewAttendanceControl | To change holiday to holiday name | NG1 | 2025-07-21 | 0.5 | Done
DailyAttendanceControl | To change employee to employee name | NG1 | 2025-07-21 | 0.5 | Done
Both | To remove default sorting rows in some columns. | NG1 | 2025-07-21 | 0.5 | Done
Both | To correct column header font size | NG1 | 2025-07-21 | 1 | Done
Both | To fix margin size. | NG1 | 2025-07-21 | 1.5 | Done
Both | To display exact number of rows | NG2 | 2025-07-21 | 1.5 | Done
Both | To change cell select colour | NG1 | 2025-07-21 | 0.5
Both | To change cell select text colour. | NG1 | 2025-07-21 | 0.5
Both | To display disabled edit buttons. | NG1 | 2025-07-21 | 0.5
Both | To change width of columns according to the content (name must be fully displayed). | NG2 | 2025-07-21 | 0.5
Edit Form | To hide table border | NG1 | 2025-07-22 | 0.5
| To make button labels (check-in/out center) | NG2 | 2025-07-22 | 0.5
| To change date time picker display (2:00 to 02:00) | NG1 | 2025-07-22 | 0.5
Check-in/out panel | To make exact size view on all dashboards | NG2 | 2025-07-22 | 2
All dashboards | To disable split panel resizable | NG1 | 2025-07-22 | 0.5
| To change split panel 2 colour | NG1 | 2025-07-22 | 0.5
| To make exact size navigation bar on all dashboards | NG1 | 2025-07-22 | 1
| To make exact button size of nav bar on all dashoards | NG1 | 2025-07-22 | 0.5
EmployeeSearchControl | To hide daily and monthly data if the search is not succeed. | NG2 | 2025-07-22 | 1.5

## LeaveManagementToFix
Control Name | Process Brief |  | Status | Planned Date | Planned Hour | Condition
LeaveRequestFormControl | To display employee suggestion based on each digit of Employee No. |  | NG2 | 2025-07-21 | 7.5
To show employee name from suggestion
|  | 1. To remove ListView user click Enter |  |  |  | Done
|  | 2. To make Scroll works along with Arrow Keys |  |  |  | Done
|  | 3. To make Search when click Enter EmployeeId manually |  |  |  | Done
|  | 4. To make Search when click Enter after choosing from ListView |  |  |  | Done
|  | 5. To fix error for showing Error Message Twice |  |  |  | Done
| To use Cancel Button to reset form for all role and previous form |  | NG1 | 2025-07-22 | 1.5
| To show MessageBox for Cancel Button |  | NG1 | 2025-07-22 | 0.25
| To change name of Apply button to Update when dericting from Detail and Update |  | NG1 | 2025-07-22 | 0.25
| To show status |  | NG1 | 2025-07-22 | 0.25
| To show department |  | NG1 | 2025-07-22 | 0.25
| To show position |  | NG1 | 2025-07-22 | 0.25
| To reload previous form correctly from Back Button |  | NG1 | 2025-07-22 | 0.25
| To show messageBox for Back Button |  | NG1 | 2025-07-22 | 0.25
ViewLeaveControl | To change Approve button's messagebox text |  | NG1 | 2025-07-22 | 0.25
| To change Revert button's messagebox text |  | NG1 | 2025-07-22 | 0.25
| Department and position columns to remove |  | NG1 | 2025-07-22 | 0.25
| To change cancel to Delete button |  | NG1 | 2025-07-22 | 0.25
| To show message box for Delete button |  | NG1 | 2025-07-22 | 0.25
| To create Reject Button Message Box |  | NG1 | 2025-07-22 | 0.5
DailyTabFor Hr and Head | Data reload incorrectly |  | NG1 | 2025-07-22 | 1
| To change Holiday Check return message |  | NG1 | 2025-07-22 | 0.5
MonthlyTabFor Hr and Head | Data reload incorrectly |  | NG1 | 2025-07-22 | 1

## LoginReportToFix
Control Name | Process Brief | Status | Planned Date | Planned Hour | Condition
Daily Attendance Summary Report | To prepare validation of present employee | NG2 | 2025-07-21 | 0.5 | Done
| To prepare validation of on leave employee | NG2 | 2025-07-21 | 0.5 | Done
| To prepare validation of absent employee | NG2 | 2025-07-21 | 0.5 | Done
| To prepare validation of early departure employee | NG2 | 2025-07-21 | 0.5 | Done
| To prepare validation of uninformed absences employee | NG2 | 2025-07-21 | 0.5 | Done
Monthly Attendance Summary Report | To prepare validation of present days | NG2 | 2025-07-21 | 0.5
| To prepare validation of working days | NG2 | 2025-07-21 | 0.5
| To prepare validation of uninformed absences employee | NG2 | 2025-07-21 | 1
| To prepare validation of late arrivals employee | NG2 | 2025-07-21 | 1
| To prepare validation of early departure employee | NG2 | 2025-07-21 | 1
| To prepare validation of overtime hours | NG2 | 2025-07-21 | 0.5
| To prepare validation of holiday overtime | NG2 | 2025-07-22 | 0.5
Login Form | Cursor Focus in password textbox | NG2 | 2025-07-22 | 0.5
| Icon in password textbox | NG2 | 2025-07-22 | 0.5
Daily Attendance Summary Report | To change form design | NG2 | 2025-07-22 | 2
| To change date time picker format | NG2 | 2025-07-22 | 0.5
| To change export button location | NG2 | 2025-07-22 | 0.5
| To change form background color if again click daily report tab | NG2 | 2025-07-22 | 1
Monthly Attendance Summary Report | To show default HR ID's data in form | NG2 | 2025-07-22 | 1
| To change size in 2 textbox | NG2 | 2025-07-22 | 1
| To change text box cursor disable | NG2 | 2025-07-22 | 0.5

## LeaveManagementToFix (2)
Control Name | Process Brief |  | Status | Planned Date | Planned Hour | Condition
LeaveRequestFormControl | To display employee suggestion based on each digit of Employee No. |  | NG2 | 2025-07-21 | 7.5 | Done
| To show employee name from suggestion |  |  |  |  | Done
|  | 1. To remove ListView user click Enter |  |  |  | Done
|  | 2. To make Scroll works along with Arrow Keys |  |  |  | Done
|  | 3. To make Search when click Enter EmployeeId manually |  |  |  | Done
|  | 4. To make Search when click Enter after choosing from ListView |  |  |  | Done
|  | 5. To fix error for showing Error Message Twice |  |  |  | Done
| To use Cancel Button to reset form for all role and previous form |  | NG1 | 2025-07-22 | 1.5
| To show MessageBox for Cancel Button |  | NG1 | 2025-07-22 | 0.25
| To change name of Apply button to Update when dericting from Detail and Update |  | NG1 | 2025-07-22 | 0.25
| To show status |  | NG1 | 2025-07-22 | 0.25
| To show department |  | NG1 | 2025-07-22 | 0.25
| To show position |  | NG1 | 2025-07-22 | 0.25
| To reload previous form correctly from Back Button |  | NG1 | 2025-07-22 | 0.25
| To show messageBox for Back Button |  | NG1 | 2025-07-22 | 0.25
ViewLeaveControl | To change Approve button's messagebox text |  | NG1 | 2025-07-22 | 0.25
| To change Revert button's messagebox text |  | NG1 | 2025-07-22 | 0.25
| Department and position columns to remove |  | NG1 | 2025-07-22 | 0.25
| To change cancel to Delete button |  | NG1 | 2025-07-22 | 0.25
| To show message box for Delete button |  | NG1 | 2025-07-22 | 0.25
| To create Reject Button Message Box |  | NG1 | 2025-07-22 | 0.5
DailyTabFor Hr and Head | Data reload incorrectly |  | NG1 | 2025-07-22 | 1
| To change Holiday Check return message |  | NG1 | 2025-07-22 | 0.5
MonthlyTabFor Hr and Head | Data reload incorrectly |  | NG1 | 2025-07-22 | 1